## CONFIG
⚙ PROJECT GANTT – CONFIGURATION CENTRE
Yellow cells are editable. All other sheets read their settings from this page via named ranges. Do NOT rename this sheet.
A ¦ PROJECT INFORMATION |  | WORKING DAYS |  |  | B ¦ ITEM TYPES ← bar colours drive the Gantt chart
Project Name | Project Alpha | Mon | 1 |  | # | Name | Bar Colour (HEX) | Text Colour (HEX) | Row BG (HEX) | Preview
Project Manager | Alice Johnson | Tue | 1 |  | 1 | Epic | 4472C4 | FFFFFF | DDEEFF | Epic
Version | 1.0 | Wed | 1 |  | 2 | Feature | ED7D31 | 000000 | FDE9D9 | Feature
Department / PMO | PMO | Thu | 1 |  | 3 | Task | 70AD47 | 000000 | E2EFDA | Task
Start Date | 2025-01-06 | Fri | 1 |  | 4 | Milestone | FF0000 | FFFFFF | FFE0E0 | Milestone
End Date | 2025-12-31 | Sat | 0 |  | 5 | Deliverable | 7030A0 | 000000 | EBD6FF | Deliverable
Working Hours / Day | 8 | Sun | 0
Currency | USD |  |  |  | C ¦ STATUSES ← colours drive conditional formatting
Gantt View Type | Weekly |  |  |  | # | Name | Colour (HEX) | Font Colour (HEX) | — | Preview
Total Budget | 500000 |  |  |  | 1 | Not Started | D9D9D9 | 000000 |  | Not Started
Contingency % | 10 |  |  |  | 2 | Planned | BDD7EE | 000000 |  | Planned
Daily Rate Multiplier | 1 |  |  |  | 3 | In Progress | FFEB9C | 000000 |  | In Progress
Show Progress Bar | 1 |  |  |  | 4 | Completed | C6EFCE | 000000 |  | Completed
[5 empty] | 5 | Delayed | FFC7CE | 000000 |  | Delayed
E ¦ GANTT DISPLAY SETTINGS |  | F ¦ PUBLIC HOLIDAYS |  |  | 6 | On Hold | FCE4D6 | 000000 |  | On Hold
Show Today Marker | 1 | Date | Description | Type | 7 | Cancelled | 808080 | 000000 |  | Cancelled
Today Marker Colour | FF0000 | 2025-01-01 | New Year's Day | Public Holiday
Weekend Colour (HEX) | F2F2F2 | 2025-04-18 | Good Friday | Public Holiday | D ¦ PRIORITIES
Milestone Symbol | ◆ | 2025-05-26 | Memorial Day | Public Holiday | # | Name | Colour (HEX) | Font Colour (HEX) | — | Preview
Deliverable Symbol | ★ | 2025-07-04 | Independence Day | Public Holiday | 1 | Low | C6EFCE | 000000 |  | Low
Gantt Row Height | 18 | 2025-09-01 | Labor Day | Public Holiday | 2 | Medium | FFEB9C | 000000 |  | Medium
Show Week Numbers | 1 | 2025-11-27 | Thanksgiving | Public Holiday | 3 | High | FFC7CE | 000000 |  | High
Bar Opacity Label | 100% | 2025-12-25 | Christmas Day | Public Holiday | 4 | Critical | FF0000 | 000000 |  | Critical
Grid Line Colour | D9D9D9
Highlight Critical | 1

## RESOURCES
👥 RESOURCE REGISTER
Define all project resources. Daily Rate = Hourly Rate × CONFIG!B11 (Working Hours/Day). Resources populate dropdowns in TASKS and RESOURCE_ALLOC.
ID | Full Name | Role | Department | Email | Avail. % | Hourly Rate | Daily Rate | Colour | Skills | Location | Contract | Notes
R01 | Alice Johnson | Project Manager | PMO | alice.johnson@company.com | 100% | 110 |  |  |  | HQ | Full-time
R02 | Bob Smith | Sr. Developer | Engineering | bob.smith@company.com | 75% | 120 |  |  |  | HQ | Full-time
R03 | Carol Williams | UX Designer | Design | carol.williams@company.com | 100% | 90 |  |  |  | HQ | Full-time
R04 | David Brown | QA Engineer | Quality | david.brown@company.com | 50% | 80 |  |  |  | HQ | Full-time
R05 | Eve Davis | Business Analyst | Business | eve.davis@company.com | 100% | 95 |  |  |  | HQ | Full-time
R06 | Frank Miller | Backend Dev | Engineering | frank.miller@company.com | 100% | 115 |  |  |  | HQ | Full-time
R07 | Grace Wilson | Frontend Dev | Engineering | grace.wilson@company.com | 75% | 100 |  |  |  | HQ | Full-time
R08 | Henry Moore | DevOps Engineer | Operations | henry.moore@company.com | 50% | 130 |  |  |  | HQ | Full-time
AVG / TOTAL

## TASKS
📋 TASK REGISTER
Enter tasks here. Dropdowns are driven by CONFIG named ranges. Duration = End − Start + 1. Up to 3 resources per task.
ID | WBS | Level | Task Name | Type | Status | Priority | Start Date | End Date | Duration (days) | Progress % | Resource 1 | R1 % | Resource 2 | R2 % | Resource 3 | R3 % | Budget | Depends On | Notes
1 | 1 | 0 | Project Kickoff | Epic | Completed | High | 2025-01-06 | 2025-01-10 |  | 100% | R01 | 80% | R05 | 20% |  |  | 3000
2 | 1.1 | 1 | Requirements Gathering | Feature | Completed | High | 2025-01-06 | 2025-01-19 |  | 100% | R01 | 80% | R05 | 20% |  |  | 8400
3 | 1.1.1 | 2 | Stakeholder Interviews | Task | Completed | Medium | 2025-01-06 | 2025-01-12 |  | 100% | R01 | 80% |  |  |  |  | 4200
4 | 1.1.2 | 2 | Document Requirements | Task | Completed | Medium | 2025-01-13 | 2025-01-19 |  | 100% | R05 | 80% |  |  |  |  | 4200
5 | 1.2 | 1 | ◆ Requirements Sign-off | Milestone | Completed | Critical | 2025-01-20 | 2025-01-20 |  | 100% | R01 | 80% |  |  |  |  | 600
6 | 2 | 0 | Design Phase | Epic | Completed | High | 2025-01-20 | 2025-02-16 |  | 100% | R03 | 80% | R05 | 20% |  |  | 16800
7 | 2.1 | 1 | UI/UX Design | Feature | Completed | High | 2025-01-20 | 2025-02-09 |  | 100% | R03 | 80% |  |  |  |  | 12600
8 | 2.1.1 | 2 | Wireframes | Task | Completed | Medium | 2025-01-20 | 2025-01-29 |  | 100% | R03 | 80% |  |  |  |  | 6000
9 | 2.1.2 | 2 | Prototypes | Task | Completed | Medium | 2025-01-30 | 2025-02-09 |  | 100% | R03 | 80% |  |  |  |  | 6600
10 | 2.2 | 1 | Architecture Design | Feature | Completed | High | 2025-01-20 | 2025-02-02 |  | 100% | R02 | 80% | R06 | 20% |  |  | 8400
11 | 2.3 | 1 | ◆ Design Review | Milestone | Completed | Critical | 2025-02-17 | 2025-02-17 |  | 100% | R01 | 80% |  |  |  |  | 600
12 | 3 | 0 | Development Sprint 1 | Epic | In Progress | High | 2025-02-17 | 2025-03-30 |  | 60% | R02 | 80% | R06 | 20% | R07 | 20% | 25200
13 | 3.1 | 1 | Backend API Development | Feature | In Progress | High | 2025-02-17 | 2025-03-16 |  | 70% | R02 | 80% | R06 | 20% |  |  | 16800
14 | 3.1.1 | 2 | User Authentication | Task | Completed | High | 2025-02-17 | 2025-02-26 |  | 100% | R06 | 80% |  |  |  |  | 6000
15 | 3.1.2 | 2 | Data Models | Task | Completed | Medium | 2025-02-27 | 2025-03-08 |  | 100% | R02 | 80% |  |  |  |  | 6000
16 | 3.1.3 | 2 | REST API Endpoints | Task | In Progress | High | 2025-03-09 | 2025-03-16 |  | 50% | R02 | 80% | R06 | 20% |  |  | 4800
17 | 3.2 | 1 | Frontend Development | Feature | In Progress | High | 2025-03-03 | 2025-03-30 |  | 40% | R07 | 80% |  |  |  |  | 16800
18 | 3.2.1 | 2 | Component Library | Task | Completed | Medium | 2025-03-03 | 2025-03-16 |  | 100% | R07 | 80% |  |  |  |  | 8400
19 | 3.2.2 | 2 | Dashboard Views | Task | In Progress | High | 2025-03-17 | 2025-03-30 |  | 30% | R07 | 80% |  |  |  |  | 8400
20 | 3.3 | 1 | ◆ Sprint 1 Review | Milestone | Planned | Critical | 2025-03-31 | 2025-03-31 |  | 0% | R01 | 80% |  |  |  |  | 600
21 | 4 | 0 | Development Sprint 2 | Epic | Planned | High | 2025-03-31 | 2025-05-11 |  | 0% | R02 | 80% | R06 | 20% | R07 | 20% | 25200
22 | 4.1 | 1 | Integration Development | Feature | Planned | High | 2025-03-31 | 2025-04-20 |  | 0% | R02 | 80% | R07 | 20% |  |  | 12600
23 | 4.2 | 1 | Performance Optimization | Feature | Planned | Medium | 2025-04-21 | 2025-05-11 |  | 0% | R06 | 80% |  |  |  |  | 12600
24 | 4.3 | 1 | ★ Sprint 2 Deliverable | Deliverable | Planned | Critical | 2025-05-12 | 2025-05-12 |  | 0% | R01 | 80% |  |  |  |  | 600
25 | 5 | 0 | Testing & QA | Epic | Planned | High | 2025-05-06 | 2025-06-02 |  | 0% | R04 | 80% | R02 | 20% |  |  | 16800
26 | 5.1 | 1 | Unit Testing | Feature | Planned | Medium | 2025-05-06 | 2025-05-19 |  | 0% | R02 | 80% |  |  |  |  | 8400
27 | 5.2 | 1 | Integration Testing | Feature | Planned | High | 2025-05-20 | 2025-06-02 |  | 0% | R04 | 80% |  |  |  |  | 8400
28 | 5.3 | 1 | UAT | Feature | Planned | High | 2025-06-03 | 2025-06-12 |  | 0% | R01 | 80% | R04 | 20% | R05 | 20% | 6000
29 | 5.4 | 1 | ◆ Testing Sign-off | Milestone | Planned | Critical | 2025-06-13 | 2025-06-13 |  | 0% | R01 | 80% |  |  |  |  | 600
30 | 6 | 0 | Deployment | Epic | Planned | Critical | 2025-06-13 | 2025-06-26 |  | 0% | R08 | 80% | R02 | 20% |  |  | 8400
31 | 6.1 | 1 | Staging Deployment | Task | Planned | High | 2025-06-13 | 2025-06-19 |  | 0% | R08 | 80% |  |  |  |  | 4200
32 | 6.2 | 1 | ★ Production Deployment | Deliverable | Planned | Critical | 2025-06-20 | 2025-06-22 |  | 0% | R08 | 80% | R01 | 20% |  |  | 1800
33 | 6.3 | 1 | ◆ Go Live | Milestone | Planned | Critical | 2025-06-23 | 2025-06-23 |  | 0% | R01 | 80% |  |  |  |  | 600
34 | 7 | 0 | Post-Launch Support | Feature | Planned | Medium | 2025-06-24 | 2025-07-07 |  | 0% | R02 | 80% | R04 | 20% |  |  | 8400
35 | 7.1 | 1 | ★ Project Closure Report | Deliverable | Planned | Medium | 2025-07-08 | 2025-07-14 |  | 0% | R01 | 80% | R05 | 20% |  |  | 4200

## GANTT_CHART
Epic |  | Feature |  | Task |  | Milestone |  | Deliverable |  |  | Not Started | Planned | In Progress | Completed | Delayed | On Hold | Cancelled
[10 empty] | Jan 2025 |  |  |  | Feb 2025 |  |  |  | Mar 2025 |  |  |  |  | Apr 2025 |  |  |  | May 2025 |  |  |  | Jun 2025 |  |  |  |  | Jul 2025 |  |  |  | Aug 2025 |  |  |  | Sep 2025 |  |  |  |  | Oct 2025 |  |  |  | Nov 2025 |  |  |  | Dec 2025
ID | WBS | Task Name | Type | Status | Start | End | Days | Done % | Resources | W01 06/01 | W02 13/01 | W03 20/01 | W04 27/01 | W05 03/02 | W06 10/02 | W07 17/02 | W08 24/02 | W09 03/03 | W10 10/03 | W11 17/03 | W12 24/03 | W13 31/03 | W14 07/04 | W15 14/04 | W16 21/04 | W17 28/04 | W18 05/05 | W19 12/05 | W20 19/05 | W21 26/05 | W22 02/06 | W23 09/06 | W24 16/06 | W25 23/06 | W26 30/06 | W27 07/07 | W28 14/07 | W29 21/07 | W30 28/07 | W31 04/08 | W32 11/08 | W33 18/08 | W34 25/08 | W35 01/09 | W36 08/09 | W37 15/09 | W38 22/09 | W39 29/09 | W40 06/10 | W41 13/10 | W42 20/10 | W43 27/10 | W44 03/11 | W45 10/11 | W46 17/11 | W47 24/11 | W48 01/12 | W49 08/12 | W50 15/12 | W51 22/12 | W52 29/12
1 | 1 | Project Kickoff | Epic | Completed | 2025-01-06 | 2025-01-10 | 5 | 100% | R01, R05 | ✓
2 | 1.1 | Requirements Gathering | Feature | Completed | 2025-01-06 | 2025-01-19 | 14 | 100% | R01, R05 | ✓ | ✓
3 | 1.1.1 | Stakeholder Interviews | Task | Completed | 2025-01-06 | 2025-01-12 | 7 | 100% | R01 | ✓
4 | 1.1.2 | Document Requirements | Task | Completed | 2025-01-13 | 2025-01-19 | 7 | 100% | R05 |  | ✓
5 | 1.2 | ◆ Requirements Sign-off | Milestone | Completed | 2025-01-20 | 2025-01-20 | 1 | 100% | R01 |  |  | ◆
6 | 2 | Design Phase | Epic | Completed | 2025-01-20 | 2025-02-16 | 28 | 100% | R03, R05 |  |  | ✓ | ✓ | ✓ | ✓
7 | 2.1 | UI/UX Design | Feature | Completed | 2025-01-20 | 2025-02-09 | 21 | 100% | R03 |  |  | ✓ | ✓ | ✓
8 | 2.1.1 | Wireframes | Task | Completed | 2025-01-20 | 2025-01-29 | 10 | 100% | R03 |  |  | ✓ | ✓
9 | 2.1.2 | Prototypes | Task | Completed | 2025-01-30 | 2025-02-09 | 11 | 100% | R03 |  |  |  | ✓ | ✓
10 | 2.2 | Architecture Design | Feature | Completed | 2025-01-20 | 2025-02-02 | 14 | 100% | R02, R06 |  |  | ✓ | ✓
11 | 2.3 | ◆ Design Review | Milestone | Completed | 2025-02-17 | 2025-02-17 | 1 | 100% | R01 | [6 empty] | ◆
12 | 3 | Development Sprint 1 | Epic | In Progress | 2025-02-17 | 2025-03-30 | 42 | 60% | R02, R06
13 | 3.1 | Backend API Development | Feature | In Progress | 2025-02-17 | 2025-03-16 | 28 | 70% | R02, R06
14 | 3.1.1 | User Authentication | Task | Completed | 2025-02-17 | 2025-02-26 | 10 | 100% | R06 | [6 empty] | ✓ | ✓
15 | 3.1.2 | Data Models | Task | Completed | 2025-02-27 | 2025-03-08 | 10 | 100% | R02 | [7 empty] | ✓ | ✓
16 | 3.1.3 | REST API Endpoints | Task | In Progress | 2025-03-09 | 2025-03-16 | 8 | 50% | R02, R06
17 | 3.2 | Frontend Development | Feature | In Progress | 2025-03-03 | 2025-03-30 | 28 | 40% | R07
18 | 3.2.1 | Component Library | Task | Completed | 2025-03-03 | 2025-03-16 | 14 | 100% | R07 | [8 empty] | ✓ | ✓
19 | 3.2.2 | Dashboard Views | Task | In Progress | 2025-03-17 | 2025-03-30 | 14 | 30% | R07
20 | 3.3 | ◆ Sprint 1 Review | Milestone | Planned | 2025-03-31 | 2025-03-31 | 1 | 0% | R01 | [12 empty] | ◆
21 | 4 | Development Sprint 2 | Epic | Planned | 2025-03-31 | 2025-05-11 | 42 | 0% | R02, R06
22 | 4.1 | Integration Development | Feature | Planned | 2025-03-31 | 2025-04-20 | 21 | 0% | R02, R07
23 | 4.2 | Performance Optimization | Feature | Planned | 2025-04-21 | 2025-05-11 | 21 | 0% | R06
24 | 4.3 | ★ Sprint 2 Deliverable | Deliverable | Planned | 2025-05-12 | 2025-05-12 | 1 | 0% | R01 | [18 empty] | ★
25 | 5 | Testing & QA | Epic | Planned | 2025-05-06 | 2025-06-02 | 28 | 0% | R04, R02
26 | 5.1 | Unit Testing | Feature | Planned | 2025-05-06 | 2025-05-19 | 14 | 0% | R02
27 | 5.2 | Integration Testing | Feature | Planned | 2025-05-20 | 2025-06-02 | 14 | 0% | R04
28 | 5.3 | UAT | Feature | Planned | 2025-06-03 | 2025-06-12 | 10 | 0% | R01, R04
29 | 5.4 | ◆ Testing Sign-off | Milestone | Planned | 2025-06-13 | 2025-06-13 | 1 | 0% | R01 | [22 empty] | ◆
30 | 6 | Deployment | Epic | Planned | 2025-06-13 | 2025-06-26 | 14 | 0% | R08, R02
31 | 6.1 | Staging Deployment | Task | Planned | 2025-06-13 | 2025-06-19 | 7 | 0% | R08
32 | 6.2 | ★ Production Deployment | Deliverable | Planned | 2025-06-20 | 2025-06-22 | 3 | 0% | R08, R01 | [23 empty] | ★
33 | 6.3 | ◆ Go Live | Milestone | Planned | 2025-06-23 | 2025-06-23 | 1 | 0% | R01 | [24 empty] | ◆
34 | 7 | Post-Launch Support | Feature | Planned | 2025-06-24 | 2025-07-07 | 14 | 0% | R02, R04
35 | 7.1 | ★ Project Closure Report | Deliverable | Planned | 2025-07-08 | 2025-07-14 | 7 | 0% | R01, R05 | [26 empty] | ★ | ★

## RESOURCE_ALLOC
📊 RESOURCE ALLOCATION MATRIX
Allocation % per resource per task. Column total > 100% = over-allocated (red). All resource names sourced from RESOURCES sheet.
ID | WBS | Task Name | Type | Alice | Bob | Carol | David | Eve | Frank | Grace | Henry | Task Total
|  |  |  | R01 | R02 | R03 | R04 | R05 | R06 | R07 | R08
1 | 1 | Project Kickoff | Epic | Alice R01: 80%; Eve R05: 20%
2 | 1.1 | Requirements Gathering | Feature | Alice R01: 80%; Eve R05: 20%
3 | 1.1.1 | Stakeholder Interviews | Task | Alice R01: 80%
4 | 1.1.2 | Document Requirements | Task | Eve R05: 80%
5 | 1.2 | Requirements Sign-off | Milestone | Alice R01: 80%
6 | 2 | Design Phase | Epic | Carol R03: 80%; Eve R05: 20%
7 | 2.1 | UI/UX Design | Feature | Carol R03: 80%
8 | 2.1.1 | Wireframes | Task | Carol R03: 80%
9 | 2.1.2 | Prototypes | Task | Carol R03: 80%
10 | 2.2 | Architecture Design | Feature | Bob R02: 80%; Frank R06: 20%
11 | 2.3 | Design Review | Milestone | Alice R01: 80%
12 | 3 | Development Sprint 1 | Epic | Bob R02: 80%; Frank R06: 20%; Grace R07: 20%
13 | 3.1 | Backend API Development | Feature | Bob R02: 80%; Frank R06: 20%
14 | 3.1.1 | User Authentication | Task | Frank R06: 80%
15 | 3.1.2 | Data Models | Task | Bob R02: 80%
16 | 3.1.3 | REST API Endpoints | Task | Bob R02: 80%; Frank R06: 20%
17 | 3.2 | Frontend Development | Feature | Grace R07: 80%
18 | 3.2.1 | Component Library | Task | Grace R07: 80%
19 | 3.2.2 | Dashboard Views | Task | Grace R07: 80%
20 | 3.3 | Sprint 1 Review | Milestone | Alice R01: 80%
21 | 4 | Development Sprint 2 | Epic | Bob R02: 80%; Frank R06: 20%; Grace R07: 20%
22 | 4.1 | Integration Development | Feature | Bob R02: 80%; Grace R07: 20%
23 | 4.2 | Performance Optimization | Feature | Frank R06: 80%
24 | 4.3 | Sprint 2 Deliverable | Deliverable | Alice R01: 80%
25 | 5 | Testing & QA | Epic | Bob R02: 20%; David R04: 80%
26 | 5.1 | Unit Testing | Feature | Bob R02: 80%
27 | 5.2 | Integration Testing | Feature | David R04: 80%
28 | 5.3 | UAT | Feature | Alice R01: 80%; David R04: 20%; Eve R05: 20%
29 | 5.4 | Testing Sign-off | Milestone | Alice R01: 80%
30 | 6 | Deployment | Epic | Bob R02: 20%; Henry R08: 80%
31 | 6.1 | Staging Deployment | Task | Henry R08: 80%
32 | 6.2 | Production Deployment | Deliverable | Alice R01: 20%; Henry R08: 80%
33 | 6.3 | Go Live | Milestone | Alice R01: 80%
34 | 7 | Post-Launch Support | Feature | Bob R02: 80%; David R04: 20%
35 | 7.1 | Project Closure Report | Deliverable | Alice R01: 80%; Eve R05: 20%
TOTAL ALLOCATION

## TIMESHEET
⏱ MONTHLY TIMESHEET
Estimated hours per resource per month, derived from allocation % × task overlap × Working Hours/Day (CONFIG!B11).
Resource | Res. ID | Task ID | Task Name | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025 | Total Hours
Alice Johnson | R01 | 1 | Project Kickoff | 22.9
Eve Davis | R05 | 1 | Project Kickoff | 5.7
Alice Johnson | R01 | 2 | Requirements Gathering | 64
Eve Davis | R05 | 2 | Requirements Gathering | 16
Alice Johnson | R01 | 3 | Stakeholder Interviews | 32
Eve Davis | R05 | 4 | Document Requirements | 32
Alice Johnson | R01 | 5 | Requirements Sign-off | 4.6
Carol Williams | R03 | 6 | Design Phase | 54.9 | 73.1
Eve Davis | R05 | 6 | Design Phase | 13.7 | 18.3
Carol Williams | R03 | 7 | UI/UX Design | 54.9 | 41.1
Carol Williams | R03 | 8 | Wireframes | 45.7
Carol Williams | R03 | 9 | Prototypes | 9.1 | 41.1
Bob Smith | R02 | 10 | Architecture Design | 54.9 | 9.1
Frank Miller | R06 | 10 | Architecture Design | 13.7 | 2.3
Alice Johnson | R01 | 11 | Design Review |  | 4.6
Bob Smith | R02 | 12 | Development Sprint 1 |  | 54.9 | 137.1
Frank Miller | R06 | 12 | Development Sprint 1 |  | 13.7 | 34.3
Grace Wilson | R07 | 12 | Development Sprint 1 |  | 13.7 | 34.3
Bob Smith | R02 | 13 | Backend API Development |  | 54.9 | 73.1
Frank Miller | R06 | 13 | Backend API Development |  | 13.7 | 18.3
Frank Miller | R06 | 14 | User Authentication |  | 45.7
Bob Smith | R02 | 15 | Data Models |  | 9.1 | 36.6
Bob Smith | R02 | 16 | REST API Endpoints |  |  | 36.6
Frank Miller | R06 | 16 | REST API Endpoints |  |  | 9.1
Grace Wilson | R07 | 17 | Frontend Development |  |  | 128
Grace Wilson | R07 | 18 | Component Library |  |  | 64
Grace Wilson | R07 | 19 | Dashboard Views |  |  | 64
Alice Johnson | R01 | 20 | Sprint 1 Review |  |  | 4.6
Bob Smith | R02 | 21 | Development Sprint 2 |  |  | 4.6 | 137.1 | 50.3
Frank Miller | R06 | 21 | Development Sprint 2 |  |  | 1.1 | 34.3 | 12.6
Grace Wilson | R07 | 21 | Development Sprint 2 |  |  | 1.1 | 34.3 | 12.6
Bob Smith | R02 | 22 | Integration Development |  |  | 4.6 | 91.4
Grace Wilson | R07 | 22 | Integration Development |  |  | 1.1 | 22.9
Frank Miller | R06 | 23 | Performance Optimization |  |  |  | 45.7 | 50.3
Alice Johnson | R01 | 24 | Sprint 2 Deliverable |  |  |  |  | 4.6
David Brown | R04 | 25 | Testing & QA |  |  |  |  | 118.9 | 9.1
Bob Smith | R02 | 25 | Testing & QA |  |  |  |  | 29.7 | 2.3
Bob Smith | R02 | 26 | Unit Testing |  |  |  |  | 64
David Brown | R04 | 27 | Integration Testing |  |  |  |  | 54.9 | 9.1
Alice Johnson | R01 | 28 | UAT | [5 empty] | 45.7
David Brown | R04 | 28 | UAT | [5 empty] | 11.4
Eve Davis | R05 | 28 | UAT | [5 empty] | 11.4
Alice Johnson | R01 | 29 | Testing Sign-off | [5 empty] | 4.6
Henry Moore | R08 | 30 | Deployment | [5 empty] | 64
Bob Smith | R02 | 30 | Deployment | [5 empty] | 16
Henry Moore | R08 | 31 | Staging Deployment | [5 empty] | 32
Henry Moore | R08 | 32 | Production Deployment | [5 empty] | 13.7
Alice Johnson | R01 | 32 | Production Deployment | [5 empty] | 3.4
Alice Johnson | R01 | 33 | Go Live | [5 empty] | 4.6
Bob Smith | R02 | 34 | Post-Launch Support | [5 empty] | 32 | 32
David Brown | R04 | 34 | Post-Launch Support | [5 empty] | 8 | 8
Alice Johnson | R01 | 35 | Project Closure Report | [6 empty] | 32
Eve Davis | R05 | 35 | Project Closure Report | [6 empty] | 8
TOTAL HOURS BY RESOURCE
|  | Resource | Total Hours
Alice Johnson
Bob Smith
Carol Williams
David Brown
Eve Davis
Frank Miller
Grace Wilson
Henry Moore

## COST_ANALYSIS
💰 COST ANALYSIS
Costs = resource daily rate (RESOURCES) × allocation % × task duration. Budget from TASKS. Currency from CONFIG.
PROJECT COST SUMMARY |  |  |  |  | COST BY RESOURCE
Total Budget |  |  |  |  | Resource | Role | Hourly Rate | Est. Hours | Est. Cost
Contingency Reserve |  |  |  |  | Alice Johnson | Project Manager | 110 | 0
Adjusted Budget |  |  |  |  | Bob Smith | Sr. Developer | 120 | 0
Estimated Resource Cost |  |  |  |  | Carol Williams | UX Designer | 90 | 0
Estimated Total Cost |  |  |  |  | David Brown | QA Engineer | 80 | 0
Budget Variance |  |  |  |  | Eve Davis | Business Analyst | 95 | 0
Budget Used % |  |  |  |  | Frank Miller | Backend Dev | 115 | 0
[5 empty] | Grace Wilson | Frontend Dev | 100 | 0
TASK-LEVEL COST BREAKDOWN
ID | WBS | Task Name | Type | Status | Start | End | Days | Budget | Resource Cost | Total Cost | Variance | Var % | Notes
1 | 1 | Project Kickoff | Epic | Completed | 2025-01-06 | 2025-01-10 | 5 | 3000 | 4280
2 | 1.1 | Requirements Gathering | Feature | Completed | 2025-01-06 | 2025-01-19 | 14 | 8400 | 11984
3 | 1.1.1 | Stakeholder Interviews | Task | Completed | 2025-01-06 | 2025-01-12 | 7 | 4200 | 4928
4 | 1.1.2 | Document Requirements | Task | Completed | 2025-01-13 | 2025-01-19 | 7 | 4200 | 4256
5 | 1.2 | Requirements Sign-off | Milestone | Completed | 2025-01-20 | 2025-01-20 | 1 | 600 | 704
6 | 2 | Design Phase | Epic | Completed | 2025-01-20 | 2025-02-16 | 28 | 16800 | 20384
7 | 2.1 | UI/UX Design | Feature | Completed | 2025-01-20 | 2025-02-09 | 21 | 12600 | 12096
8 | 2.1.1 | Wireframes | Task | Completed | 2025-01-20 | 2025-01-29 | 10 | 6000 | 5760
9 | 2.1.2 | Prototypes | Task | Completed | 2025-01-30 | 2025-02-09 | 11 | 6600 | 6336
10 | 2.2 | Architecture Design | Feature | Completed | 2025-01-20 | 2025-02-02 | 14 | 8400 | 13328
11 | 2.3 | Design Review | Milestone | Completed | 2025-02-17 | 2025-02-17 | 1 | 600 | 704
12 | 3 | Development Sprint 1 | Epic | In Progress | 2025-02-17 | 2025-03-30 | 42 | 25200 | 46704
13 | 3.1 | Backend API Development | Feature | In Progress | 2025-02-17 | 2025-03-16 | 28 | 16800 | 26656
14 | 3.1.1 | User Authentication | Task | Completed | 2025-02-17 | 2025-02-26 | 10 | 6000 | 7360
15 | 3.1.2 | Data Models | Task | Completed | 2025-02-27 | 2025-03-08 | 10 | 6000 | 7680
16 | 3.1.3 | REST API Endpoints | Task | In Progress | 2025-03-09 | 2025-03-16 | 8 | 4800 | 7616
17 | 3.2 | Frontend Development | Feature | In Progress | 2025-03-03 | 2025-03-30 | 28 | 16800 | 17920
18 | 3.2.1 | Component Library | Task | Completed | 2025-03-03 | 2025-03-16 | 14 | 8400 | 8960
19 | 3.2.2 | Dashboard Views | Task | In Progress | 2025-03-17 | 2025-03-30 | 14 | 8400 | 8960
20 | 3.3 | Sprint 1 Review | Milestone | Planned | 2025-03-31 | 2025-03-31 | 1 | 600 | 704
21 | 4 | Development Sprint 2 | Epic | Planned | 2025-03-31 | 2025-05-11 | 42 | 25200 | 46704
22 | 4.1 | Integration Development | Feature | Planned | 2025-03-31 | 2025-04-20 | 21 | 12600 | 19488
23 | 4.2 | Performance Optimization | Feature | Planned | 2025-04-21 | 2025-05-11 | 21 | 12600 | 15456
24 | 4.3 | Sprint 2 Deliverable | Deliverable | Planned | 2025-05-12 | 2025-05-12 | 1 | 600 | 704
25 | 5 | Testing & QA | Epic | Planned | 2025-05-06 | 2025-06-02 | 28 | 16800 | 19712
26 | 5.1 | Unit Testing | Feature | Planned | 2025-05-06 | 2025-05-19 | 14 | 8400 | 10752
27 | 5.2 | Integration Testing | Feature | Planned | 2025-05-20 | 2025-06-02 | 14 | 8400 | 7168
28 | 5.3 | UAT | Feature | Planned | 2025-06-03 | 2025-06-12 | 10 | 6000 | 9840
29 | 5.4 | Testing Sign-off | Milestone | Planned | 2025-06-13 | 2025-06-13 | 1 | 600 | 704
30 | 6 | Deployment | Epic | Planned | 2025-06-13 | 2025-06-26 | 14 | 8400 | 14336
31 | 6.1 | Staging Deployment | Task | Planned | 2025-06-13 | 2025-06-19 | 7 | 4200 | 5824
32 | 6.2 | Production Deployment | Deliverable | Planned | 2025-06-20 | 2025-06-22 | 3 | 1800 | 3024
33 | 6.3 | Go Live | Milestone | Planned | 2025-06-23 | 2025-06-23 | 1 | 600 | 704
34 | 7 | Post-Launch Support | Feature | Planned | 2025-06-24 | 2025-07-07 | 14 | 8400 | 12544
35 | 7.1 | Project Closure Report | Deliverable | Planned | 2025-07-08 | 2025-07-14 | 7 | 4200 | 5992
TOTAL

## CHANGE_LOG
📝 CHANGE LOG
Date | Version | Changed By | Sheet | Cell/Range | Old Value | New Value | Reason / Notes
2026-03-26 | 1.0 | Alice Johnson | CONFIG | B5 |  | Project Alpha | Initial workbook setup

## INSTRUCTIONS
ℹ️ HOW TO USE THIS WORKBOOK
Sheet | Purpose / What to edit | Inputs? | Formulas? | Linked to
CONFIG | Master control panel. Set project name, dates, view type, currency, budget. Define type/status/priority colours. Add holidays. ALL other sheets read from here via named ranges. | YES – yellow cells | Partial | All sheets
RESOURCES | Add team members, roles, hourly rates, availability. Daily Rate auto-calculates from CONFIG hours/day. | YES | Daily Rate | TASKS, TIMESHEET, COST
TASKS | Enter all tasks. Dropdowns for Type/Status/Priority/Resources are driven by CONFIG & RESOURCES named ranges. Duration is a formula. | YES | Duration | GANTT, ALLOC, TIME, COST
GANTT_CHART | Read-only visual timeline. 52-week view. Bars coloured by item type. Darker=completed portion. ◆=Milestone ★=Deliverable. Red column=Today. | No | Yes | TASKS, CONFIG
RESOURCE_ALLOC | % allocation matrix. Column totals > 100% turn red (over-allocated). All names from RESOURCES. | Adjust % | Totals | RESOURCES, TASKS
TIMESHEET | Monthly estimated hours per resource per task, based on allocation % and task date overlap. | Adjust hrs | Yes | TASKS, RESOURCES, CONFIG
COST_ANALYSIS | Task budget vs resource cost breakdown. Green variance = under budget. Red = over. Summary reads budget from CONFIG. | No | Yes | TASKS, RESOURCES, CONFIG
CHANGE_LOG | Record plan changes. Track version, who changed what cell, old/new values, and reason. | YES | No | —
KEY CONFIG RULES | ✅ Change colours in CONFIG → they appear in Preview column immediately.
✅ Add rows to RESOURCES → they appear in TASKS resource dropdowns automatically.
✅ Gantt View (CONFIG B13): Daily / Weekly / Monthly changes the header description.
✅ Currency (CONFIG B12): shown in COST summary label.
✅ Working Hours/Day (CONFIG B11): drives Daily Rate in RESOURCES.
✅ Holidays (CONFIG Section F): used with NETWORKDAYS formulas.
✅ Budget (CONFIG B14) + Contingency % (B15) → Adjusted Budget in COST.
NAMED RANGES | CFG_ProjectName, CFG_StartDate, CFG_EndDate, CFG_HoursPerDay, CFG_Currency, CFG_GanttView, CFG_Budget, CFG_Contingency
ItemTypeNames, StatusNames, PriorityNames (drive all dropdowns)
ResourceNames, ResourceIDs, ResourceRates, ResourceAvail
TaskIDs, TaskNames, TaskStartDates, TaskEndDates, TaskProgress